## Status Report
Status Report for Team 6
Project | MealMate | Status: (Red/Yellow/Green)
Date: | 2024-10-21 | Overall Status: | Green
Contact: | eliott.wantz@mthree.com | Explanation: | We added the main use cases, and are creating our diagrams (flow charts, UML, ERD). This gives us a solid foundation to build on.
Prepared By: | Eliott Wantz
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Team | Define our project and main objective
Team | Get project approuval
Team | Define & assign tasks
ID # | Key Issues | Action Plan |  |  | Status
None
Critical Milestones |  | Health | Due Date | Comment/Status %
Defining use cases |  | Green | 2024-10-21 | 100%
ERD |  | Green | 2024-10-21 | 35%
Database script |  | Green | 2024-10-21 | 100%
UML |  | Green | 2024-10-21 | 40%
Flow Chart |  | Green | 2024-10-21 | 50%
Recipe dao |  | Green | 2024-10-22 | 0%
User dao |  | Green | 2024-10-22 | 0%
User controller |  | Green | 2024-10-22 | 0%
Recipe controller |  | Green | 2024-10-22 | 0%
User service |  | Green | 2024-10-23 | 0%
Recipe service |  | Green | 2024-10-23 | 0%
Test daos |  | Green | 2024-10-23 | 0%
Test services |  |  | 2024-10-24 | 0%
Prepare the final presentation |  | Green | 2024-10-24 | 0%
Stretch Goal -> Frontend |  | Green | 2024-10-24 | 0%