## Status Report
Status Report for Team 6
Project | MealMate | Status: (Red/Yellow/Green)
Date: | 2024-10-23 | Overall Status: | Green
Contact: | colin.woelfel@mthree.com | Explanation: | We have finished the DAOs and DTOs, now we are working on finishing the ServiceLayer, Controller, and Testing.
Prepared By: | Colin Woelfel
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Team | Define our project and main objective
Team | Get project approuval
Team | Define & assign tasks
Team | implemented Project Skeleton
Team | Updated ERD design
Team | Completed DAOs and DTOs
ID # | Key Issues | Action Plan |  |  | Status
1 | confusion with how API works | revisted ERD and tested some queires to better understand API |  |  | green
2 | merge conflict in git | used git checkout to merge branches and resolve conflict |  |  | green
Critical Milestones |  | Health | Due Date | Comment/Status %
Defining use cases |  | Green | 2024-10-21 | 100%
ERD |  | Green | 2024-10-21 | 100%
Database script |  | Green | 2024-10-21 | 100%
UML |  | Green | 2024-10-21 | 100%
frontend mockup |  | Green | 2024-10-22 | 100%
Recipe DAO |  | Green | 2024-10-22 | 100%
User DAO |  | Green | 2024-10-22 | 100%
ingredient DAO |  | Green | 2024-10-22 | 100%
DTO recipe |  | Green | 2024-10-22 | 100%
DTO ingredient |  | Green | 2024-10-22 | 100%
DTO User |  | Green | 2024-10-22 | 100%
DTO recipe ingredients |  | Green | 2024-10-22 | 100%
User service |  | Green | 2024-10-23 | 100%
Recipe service |  | yellow | 2024-10-23 | 80%
Recipe controller |  | Green | 2024-10-23 | 100%
Test daos |  | yellow | 2024-10-24 | 20%
Test services |  | yellow | 2024-10-24 | 20%
Prepare the final presentation |  | yellow | 2024-10-24 | 30%
Stretch Goal -> Frontend