## Status Report
Status Report for Team 6
Project | MealMate | Status: (Red/Yellow/Green)
Date: | 2024-10-24 | Overall Status: | Green
Contact: | shuyuan.zhang@mthree.com | Explanation: | We have finished the DAOs, DTOs, Services and Controllers. User module and related tests are done. Now we are working on Recipe Module's debugging and testing.
Prepared By: | Shuyuan Zhang
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Team | Define our project and main objective
Team | Get project approuval
Team | Define & assign tasks
Team | implemented Project Skeleton
Team | Updated ERD design
Team | Completed DAOs and DTOs
Team | Completed Services and Controllers
ID # | Key Issues | Action Plan |  |  | Status
1 | confusion with how API works | revisted ERD and tested some queires to better understand API |  |  | green
2 | merge conflict in git | used git checkout to merge branches and resolve conflict |  |  | green
3 | SQL syntax errors | corrected them by group discussions |  |  | green
4 | RecipeDAO testing issues | fixing them by group debugging meetings |  |  | yellow
Critical Milestones |  | Health | Due Date | Comment/Status %
Defining use cases |  | Green | 2024-10-21 | 100%
ERD |  | Green | 2024-10-21 | 100%
Database script |  | Green | 2024-10-21 | 100%
UML |  | Green | 2024-10-21 | 100%
frontend mockup |  | Green | 2024-10-22 | 100%
Recipe DAO |  | Green | 2024-10-22 | 100%
User DAO |  | Green | 2024-10-22 | 100%
ingredient DAO |  | Green | 2024-10-22 | 100%
DTO recipe |  | Green | 2024-10-22 | 100%
DTO ingredient |  | Green | 2024-10-22 | 100%
DTO User |  | Green | 2024-10-22 | 100%
DTO recipe ingredients |  | Green | 2024-10-22 | 100%
User service |  | Green | 2024-10-23 | 100%
Recipe service |  | yellow | 2024-10-23 | 90%
Recipe controller |  | Green | 2024-10-23 | 100%
User controller |  | Green | 2024-10-24 | 100%
Test daos |  | yellow | 2024-10-24 | 75%
Test services |  | yellow | 2024-10-24 | 50%
Prepare the final presentation |  | yellow | 2024-10-24 | 50%
Stretch Goal -> Frontend